## COTS
Risk Category |  | Ref # | Risk Description | Vulnerabilities / Predisposing Characteristics | Current Controls / Mitigating Factors | Likelihood | Impact | Risk | Comments
ERP Implementation and Organisation Related Risk |  | R1 | Inadequate enterprise resources for governance and oversight (e.g. Board, Audit Committee, Legal Counsel, Enterprise Risk Management) | Limited project management skills Insufficient IT infrastructure Inadequate cybersecurity expertise and technology | Clearly documented business, functionality, and security requirements Contract with the vendor, including roles & responsibilities and terms & conditions. Cloud service with inbuilt cybersecurity and resilient configuration options. | Highly Likely | Considerable | 4
|  | R2 | Customisation and modification result in ongoing maintenance challenges |  |  | Highly Unlikely | Negligible | 1
|  | R3 | Inability to integrate with existing systems can lead to data exchange and data duplication issues |  |  | Highly Unlikely | Negligible | 1
|  | R4 | Resistance to change or accept the system and process change leads to cost overruns |  |  | Highly Unlikely | Negligible | 1
Project Management Related Risks |  | R5 | Significant costs related to project management resources: IT personnel, specialists related project management |  |  | Highly Unlikely | Negligible | 1
|  | R6 | Costly initial investments: Servers, databases, cloud services, and other supporting systems |  |  | Highly Unlikely | Negligible | 1
|  | R7 | Expensive ongoing management: Training, support, maintenance and change management |  |  | Highly Likely | Considerable | 4
|  | R8 | Significant time required for project implementation: Requirements gathering to user training |  |  | Highly Unlikely | Negligible | 1
|  | R9 | Poor quality: Functionalities, user-friendly interfaces, and ability to use with minimal configurations |  |  | Highly Unlikely | Negligible | 1
SDLC Related Risks | System Analysis and Requirements | R10 | Inadequate system analysis and requirements: Threat/vulnerability analysis, assets identification & rating and existing controls |  |  | Highly Likely | Considerable | 4
|  | R11 | Insufficient documentation with necessary details |  |  | Highly Likely | Considerable | 4
| System Design | R12 | Poor and incorrect selection of architecture approach, design approach, programming languages and methodologies |  |  | Highly Unlikely | Negligible | 1
|  | R13 | Incomplete design documents with insufficient detail |  |  | Highly Unlikely | Negligible | 1
| Development | R14 | Incomplete designs |  |  | Highly Unlikely | Negligible | 1
|  | R15 | Insufficient expertise in development/programming |  |  | Highly Unlikely | Negligible | 1
|  | R16 | Inadequate documentation to support the code |  |  | Highly Unlikely | Negligible | 1
|  | R17 | Incomplete unit tests which do not reflect the requirements |  |  | Highly Unlikely | Negligible | 1
|  | R18 | Technical errors or omissions |  |  | Highly Unlikely | Negligible | 1
|  | R19 | The rapid pace of technological change can create challenges |  |  | Highly Unlikely | Negligible | 1
| Testing | R20 | Incompatible components |  |  | Highly Unlikely | Negligible | 1
|  | R21 | Missing functionality |  |  | Highly Unlikely | Negligible | 1
|  | R22 | Inadequate documentation with new requirements based on the testing |  |  | Highly Unlikely | Negligible | 1
| Installation and UAT | R23 | User issues may not be identified promptly |  |  | Highly Unlikely | Negligible | 1
|  | R24 | Environmental incompatibilities |  |  | Highly Unlikely | Negligible | 1
|  | R25 | UAT failure or fail to meet user requirements |  |  | Highly Unlikely | Negligible | 1
| Ops and Maintenance | R26 | Inadequate training |  |  | Highly Unlikely | Negligible | 1
|  | R27 | Insufficient resources to support the solution |  |  | Highly Unlikely | Negligible | 1
|  | R28 | Lack of maintenance and updates: Patching, Upgrading and Vulnerability Management |  |  | Highly Unlikely | Negligible | 1
Security and Availability |  | R29 | Coordinate cyber-attacks using various attack vectors such as external, internal, and supply chain |  |  | Highly Unlikely | Negligible | 1
|  | R30 | The solution may not be available due to human error or natural disaster |  |  | Highly Unlikely | Negligible | 1
Total Risk | [7 empty] | 42

## Open
Risk Category |  | Ref # | Risk Description | Vulnerabilities / Predisposing Characteristics | Current Controls / Mitigating Factors | Likelihood | Impact | Risk | Comments
ERP Implementation and Organisation Related Risk |  | R1 | Inadequate enterprise resources for governance and oversight (e.g. Board, Audit Committee, Legal Counsel, Enterprise Risk Management) | Limited project management skills Insufficient IT infrastructure Inadequate cybersecurity expertise and technology | Developed and tested by communities of users and developers Guidance from the communities Clear understating of business and requirements | Highly Likely | Considerable | 4
|  | R2 | Customisation and modification result in ongoing maintenance challenges |  |  | Possible | Acceptable | 2
|  | R3 | Inability to integrate with existing systems can lead to data exchange and data duplication issues |  |  | Possible | Acceptable | 2
|  | R4 | Resistance to change or accept the system and process change leads to cost overruns |  |  | Possible | Acceptable | 2
Project Management Related Risks |  | R5 | Significant costs related to project management resources: IT personnel, specialists related project management |  |  | Possible | Acceptable | 2
|  | R6 | Costly initial investments: Servers, databases, cloud services, and other supporting systems |  |  | Possible | Acceptable | 2
|  | R7 | Expensive ongoing management: Training, support, maintenance and change management |  |  | Highly Unlikely | Negligible | 1
|  | R8 | Significant time required for project implementation: Requirements gathering to user training |  |  | Possible | Acceptable | 2
|  | R9 | Poor quality: Functionalities, user-friendly interfaces, and ability to use with minimal configurations |  |  | Possible | Acceptable | 2
SDLC Related Risks | System Analysis and Requirements | R10 | Inadequate system analysis and requirements: Threat/vulnerability analysis, assets identification & rating and existing controls |  |  | Highly Unlikely | Negligible | 1
|  | R11 | Insufficient documentation with necessary details |  |  | Highly Unlikely | Negligible | 1
| System Design | R12 | Poor and incorrect selection of architecture approach, design approach, programming languages and methodologies |  |  | Possible | Acceptable | 2
|  | R13 | Incomplete design documents with insufficient detail |  |  | Possible | Acceptable | 2
| Development | R14 | Incomplete designs |  |  | Possible | Acceptable | 2
|  | R15 | Insufficient expertise in development/programming |  |  | Possible | Acceptable | 2
|  | R16 | Inadequate documentation to support the code |  |  | Possible | Acceptable | 2
|  | R17 | Incomplete unit tests which do not reflect the requirements |  |  | Possible | Acceptable | 2
|  | R18 | Technical errors or omissions |  |  | Possible | Acceptable | 2
|  | R19 | The rapid pace of technological change can create challenges |  |  | Possible | Acceptable | 2
| Testing | R20 | Incompatible components |  |  | Possible | Acceptable | 2
|  | R21 | Missing functionality |  |  | Possible | Acceptable | 2
|  | R22 | Inadequate documentation with new requirements based on the testing |  |  | Possible | Acceptable | 2
| Installation and UAT | R23 | User issues may not be identified promptly |  |  | Possible | Acceptable | 2
|  | R24 | Environmental incompatibilities |  |  | Possible | Acceptable | 2
|  | R25 | UAT failure or fail to meet user requirements |  |  | Possible | Acceptable | 2
| Ops and Maintenance | R26 | Inadequate training |  |  | Possible | Acceptable | 2
|  | R27 | Insufficient resources to support the solution |  |  | Possible | Acceptable | 2
|  | R28 | Lack of maintenance and updates: Patching, Upgrading and Vulnerability Management |  |  | Possible | Acceptable | 2
Security and Availability |  | R29 | Coordinate cyber-attacks using various attack vectors such as external, internal, and supply chain |  |  | Possible | Acceptable | 2
|  | R30 | The solution may not be available due to human error or natural disaster |  |  | Possible | Acceptable | 2
Total Risk | [7 empty] | 59

## In-House
Risk Category |  | Ref # | Risk Description | Vulnerabilities / Predisposing Characteristics | Current Controls / Mitigating Factors | Likelihood | Impact | Risk | Comments
ERP Implementation and Organisation Related Risk |  | R1 | Inadequate enterprise resources for governance and oversight (e.g. Board, Audit Committee, Legal Counsel, Enterprise Risk Management) | Limited project management skills Insufficient IT infrastructure Inadequate cybersecurity expertise and technology | Clear understating of business and requirements | Highly Likely | Considerable | 4
|  | R2 | Customisation and modification result in ongoing maintenance challenges |  |  | Highly Likely | Considerable | 4
|  | R3 | Inability to integrate with existing systems can lead to data exchange and data duplication issues |  |  | Highly Likely | Considerable | 4
|  | R4 | Resistance to change or accept the system and process change leads to cost overruns |  |  | Highly Likely | Considerable | 4
Project Management Related Risks |  | R5 | Significant costs related to project management resources: IT personnel, specialists related project management |  |  | Highly Likely | Considerable | 4
|  | R6 | Costly initial investments: Servers, databases, cloud services, and other supporting systems |  |  | Highly Likely | Considerable | 4
|  | R7 | Expensive ongoing management: Training, support, maintenance and change management |  |  | Highly Unlikely | Negligible | 1
|  | R8 | Significant time required for project implementation: Requirements gathering to user training |  |  | Highly Likely | Considerable | 4
|  | R9 | Poor quality: Functionalities, user-friendly interfaces, and ability to use with minimal configurations |  |  | Highly Likely | Considerable | 4
SDLC Related Risks | System Analysis and Requirements | R10 | Inadequate system analysis and requirements: Threat/vulnerability analysis, assets identification & rating and existing controls |  |  | Highly Unlikely | Negligible | 1
|  | R11 | Insufficient documentation with necessary details |  |  | Highly Unlikely | Negligible | 1
| System Design | R12 | Poor and incorrect selection of architecture approach, design approach, programming languages and methodologies |  |  | Highly Likely | Considerable | 4
|  | R13 | Incomplete design documents with insufficient detail |  |  | Highly Likely | Considerable | 4
| Development | R14 | Incomplete designs |  |  | Highly Likely | Considerable | 4
|  | R15 | Insufficient expertise in development/programming |  |  | Highly Likely | Considerable | 4
|  | R16 | Inadequate documentation to support the code |  |  | Highly Likely | Considerable | 4
|  | R17 | Incomplete unit tests which do not reflect the requirements |  |  | Highly Likely | Considerable | 4
|  | R18 | Technical errors or omissions |  |  | Highly Likely | Considerable | 4
|  | R19 | The rapid pace of technological change can create challenges |  |  | Highly Likely | Considerable | 4
| Testing | R20 | Incompatible components |  |  | Highly Likely | Considerable | 4
|  | R21 | Missing functionality |  |  | Highly Likely | Considerable | 4
|  | R22 | Inadequate documentation with new requirements based on the testing |  |  | Highly Likely | Considerable | 4
| Installation and UAT | R23 | User issues may not be identified promptly |  |  | Highly Likely | Considerable | 4
|  | R24 | Environmental incompatibilities |  |  | Highly Likely | Considerable | 4
|  | R25 | UAT failure or fail to meet user requirements |  |  | Highly Likely | Considerable | 4
| Ops and Maintenance | R26 | Inadequate training |  |  | Highly Likely | Considerable | 4
|  | R27 | Insufficient resources to support the solution |  |  | Highly Likely | Considerable | 4
|  | R28 | Lack of maintenance and updates: Patching, Upgrading and Vulnerability Management |  |  | Highly Likely | Considerable | 4
Security and Availability |  | R29 | Coordinate cyber-attacks using various attack vectors such as external, internal, and supply chain |  |  | Highly Likely | Considerable | 4
|  | R30 | The solution may not be available due to human error or natural disaster |  |  | Highly Likely | Considerable | 4
Total Risk | [7 empty] | 111